## Work Process
\
Green |  | Tee - Off |  | Bunker |  | Fair way
[6 empty] | Trenching | Main drain
Pipe installation
A: INSPECTION
Back Fill
[6 empty] | Trenching | Irrigation
Pipe installation
B: INSPECTION
Back Fill
Trenching | Sub Surface drain | Trenching | Sub Surface drain | Trenching | Sub Surface drain | Trenching | Sub Surface drain
Geotextile installation |  | Geotextile installation |  | Geotextile installation
Pipe installation |  | Pipe installation |  | Pipe installation |  | Pipe installation
C: INSPECTION |  | C: INSPECTION |  | C: INSPECTION |  | C: INSPECTION
Gravel Back Fill |  | Gravel Back Fill |  | Gravel Back Fill |  | Gravel Back Fill
Sand Cap |  | Sand Cap |  | Sand Cap |  | Sand Cap
D: INSPECTION |  | D: INSPECTION |  |  |  | D: INSPECTION
Grassing |  | Grassing |  |  |  | Grassing
พื้นที่ Green |  | พื้นที่ Tee - Off |  | พื้นที่ Bunker |  | พื้นที่ Fair way
FM-OP-08 (Golf-05), 21/08/23
INSPECTION
Golf Course Construction Work Process
Request for Inspection (RFIn)
A
B
C
D

## Ins.
INSPECTION LAYER |  | GREEN | TEE | BUNKER | FAIR WAY
A | Request for Material Back Fill After Main Drain System (only Fair Way) | - | - | - | ü
B | Request for Material Back Fill After Irrigation System (only Fairway + Rough) | - | - | - | ü
C | Request for Material Back Fill After Sub Surface Drain System (Tee off, Fairway, Green and Buker) | ü | ü | ü | ü
D | Request for Grassing (Tee off, Fair Way and Green) | ü | ü | - | ü
Update : 24-05-2019: Rev.04